## Sheet1
# | Issue | Description | Priority | Assigned To | Status | Start Date | Expected Due Date
1 | Allow people to use docker to run the API | Dockerize the application so that the mongodb instance and api server run togethor on spinning up the container | Medium | Muhammad | Done | 2023-01-14 | 2023-01-18
2 | Add commenting feature | Add GET,POST routes for querying and adding comments from/to specific posts | Medium | Muhammad | Ongoing | 2023-01-24 | 2023-02-12
3 | All API should have the same structure for response | Clients need to consume the api predictably and all responses should have the same JSON structure | Low | Muhammad | To-do | 2023-01-30 | 2023-02-27
4 | Implement unit testing for the API | No unit tests written for the project, need to implement tests for the routes | High | Hyunchul | To-do | 2023-02-01 | 2023-02-15
5 | Extract services from the controller | Extract services to reduce coupling in the logic and presenting controller | Medium | Hyunchul | Ongoing | 2023-01-28 | 2023-02-04